## Sheet1
Báo cáo tổng hợp tiến độ thực hiện Khóa luận tốt nghiệp Spring 2023
Giảng viên: | Nguyễn Quốc Trung
Bộ môn:
| Topic | Lịch hẹn SV | Tiến độ thực hiện
|  | (giờ-ngày trong tuần) | Tuần 1 | Tuần 2 | Tuần 3 | Tuần 4 | Tuần 5 | Tuần 6 | Tuần 7 | Tuần 8 | Tuần 9 | Tuần 10 | Tuần 11 | Tuần 12 | Tuần 13 | Tuần 14
| Deep Learning in Age-Invariant Face Recognition - Nhận dạng khuôn mặt bất biến theo thời gian bằng học sâu | 8h tối thứ 6 | Research on topic | Research on topic | Choose Scope for Proposal | preliminary test | Code Transfer Learning and Hyperparameter Tuning for ML algorithm, Data preprocessing,... | Code Transfer Learning and Hyperparameter Tuning for Resnet,Evaluate Resnet models on FGNet with generated images from SAM face aging model,... | Complete code and hyperparameter tuning for BYOL, Run and collect the results of Transfer Learning Resnet model,... | Train resnet models on datasets with generated images, Run and collect the results of Transfer Learning Resnet model,... | Train and fine-tune model BYOL on FGnet dataset, Fine-tuning CUSP model to generate high preservation face aging images,Create a Web Demo | Train and fine-tune model BYOL on CACD dataset, Train ResNet models on datasets with generated images,... | Research and analyze existing results | write paper, report, making slide | Write paper, report, making slide | Complete report and slide
Tuần 1: | Phê duyệt KH chi tiết thực hiện khóa luận, supervisor phê duyệt
Tuần 13: | Phê duyệt bảo vệ khóa luận: supervisor đề nghị, CNBM xem xét và phê duyệt
- Fail: toàn bộ nhóm
- OK, với danh sách SV (có thể có SV không được bảo vệ)

## Sheet2
Báo cáo chi tiết:
Code: | SP23A10
Topic: | Deep Learning in Age-Invariant Face Recognition - Nhận dạng khuôn mặt bất biến theo thời gian bằng học sâu
MSSV | Họ tên SV | Phân công |  |  | Tiến độ thực hiện
|  | Nhiệm vụ 1 | Nhiệm vụ 2 | Nhiệm vụ 3 | Tuần 1 | Tuần 2 | Tuần 3 | Tuần 4 | Tuần 5 | Tuần 6 | Tuần 7 | Tuần 8 | Tuần 9 | Tuần 10 | Tuần 11 | Tuần 12 | Tuần 13 | Tuần 14
SE151488 | Lê Quang Minh | Machine Learning | Train BYOL on FGnet Dataset | Train BYOL on CACD dataset | Research on topic | Research on topic | Choose Scope | Preliminary test | Code Transfer Learning and Hyperparameter Tuning for ML algorithm | Run and collect the results of ML model | Complete code and hyperparameter tuning for BYOL | Train and fine-tune model BYOL on FGnet dataset | Train and fine-tune model BYOL on FGnet dataset | Train and fine-tune model BYOL on CACD dataset | Research results | write paper, report | write paper, report | complete paper, report
SE150215 | Tôn Nữ Quyền Mi | Data Preprocessing | Train ResNet model on both datasets | Build web demo | Resreach on topic | Research on topic | Choose Scope | Preliminary test | Data Preprocessing | Code Transfer Learning and Hyperparameter Tuning for Resnet | Run and collect the results of Transfer Learning Resnet model on FGNet dataset | Run and collect the results of Transfer Learning Resnet model on CACD dataset | Create a Web Demo | Complete web demo | Research results | write paper, report | write paper, report | complete report, paper
SE151345 | Nguyễn Lâm Nguyên | Face alignment on datasets | Using generative model to generate images | Test models' performance on generated images | Research on topic | Research on topic | Choose Scope | Preliminary test | Face alignment | Evaluate Resnet models on FGNet with generated images from SAM face aging model | Using CUSP to generate face images on FGNet and CACD dataset | Train resnet models on datasets with generated images | Tuning CUSP model to generate high preservation face aging images on FGNet and CACD | Train ResNet models on datasets with generated images | Research results | write paper, report | making slide | complete slide